## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. |  | O.H. 03/04/2025
| Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. |  | O.H. 03/04/2025
| Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute. |  | O.H. 03/04/2025
| Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. |  | O.H. 03/04/2025
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. |  | O.H. 03/04/2025
As a helper I want to add a need to my funding basket so that I can decide to fund it later. | Given I am logged in, when I click add on a need, it will update my basket with the new need. |  | J.D. 03/05/2025
As a Helper, I want to remove a need from my funding basket so that I can update my funding preferences. | Given I am viewing my basket, when I click remove on a need, the basket should update with the need removed. |  | J.D. 03/05/2025
As a Helper, I want to be able to authorize with the system so I can manage my basket. | Given I enter valid credentials, when I press login, I should see my basket. |  | L.W 03/13/2025
| Given I enter invalid credentials, when I press login, I expect to see an error message. |  | L.W 03/13/2025
As a U-fund Manager, I want to authorize with the system so I can manage the organization’s cupboard. | Given I enter valid credentials, when I press login, I should see the organization's cupboard. |  | A.L 03/14/2025
| Given I enter invalid credentials, when I press login, I expect to see an error message. |  | A.L 03/14/2025
As a Helper, I want to be able to search for needs so I can find a specific need quickly. | Given a need exists when I search for that need I expect the need to be previewed |  | O.H 03/06/2025
| Given a need does not exist when I search for a nonexistent need then I expect a return of nothing found |  | O.H 03/06/2025
As a U-fund Manager, I want to remove a fulfilled or irrelevant need from the cupboard so that Helpers do not see outdated needs. | Given I submit a request to remove a product that has already been fulfilled or outdated when the product exists then the product should be removed from the cupboard and the system should return a status code of 200 (OK) |  | V.U. 03/07/2025
| Given I submit a request to remove a product that has already been fulfilled or outdated when the product does not exist then the system should return a status code of 404 (NOT FOUND). |  | V.U 03/07/2025
As a Helper, I want to be able to authorize with the system so I can manage my basket. | Given I enter valid credentials, when I press login, I should see my basket. |  | L.W 03/15/2025
| Given I enter invalid credentials, when I press login, I expect to see an error message. |  | L.W 03/15/2025
As a Helper, I want to check out and fund all selected needs in my funding basket so that my contributions are submitted. | given that I have selected needs in my funding basket when I proceed to checkout then I expect to see a summary of the selected needs and their total cost
given that I am ready to fund the selected needs when I confirm the checkout then I expect my contributions to be submitted successfully
given that I have insufficient funds when I try to check out then I expect to see an error message indicating insufficient funds
As a U-fund Manager, I want to be able to search for needs so I can find a specific need quickly. | GIVEN I submit a request to search for a specific need in my cupboard WHEN there is a need that contains that text, THEN the system should return a list of needs containing only needs that contain the text and a status code of OK.
GIVEN I submit a request to search for a specific need in my cupboard WHEN there are no needs that contains that text, THEN the system should return an empty list and a status code of OK.
**NOT IMPLEMENTED YET** As a Helper, I want to be able to save needs to a wish list so I can revisit needs that I have interest in in the future. | Given I am logged in as a helper, when I click add need to wishlist, my wishlist should be updated with the added need.
Given I am viewing my wishlist, when I add the need to my basket, the need should be moved from my wishlist into my basket.
**NOT IMPLEMENTED YET** As a Helper, I want to remove needs from my wish list in case I will not be able to afford them in the future. | Given I am logged in as a helper when I click remove on a need in my wishlist then the need will be removed from my wishlist.
**NOT IMPLEMENTED YET** As a Helper, I want to view my wish list so I can see the needs I have saved for purchasing later | given that I have items in my wish list when I view my wish list then I expect to see a list of all the needs I have saved for later
given that my wish list is empty when I view it then I expect to see a message indicating that the wish list is empty
given that I have items in my wish list when I remove an item then I expect that item to be removed from the wish list
**NOT IMPLEMENTED YET** As a Helper, I would like to filter my searches based on whether or not I’ve viewed them before so I can browse needs I have not seen. | given that there are both viewed and unviewed needs when I filter for unviewed needs then I expect to see only needs I have not seen before
given that there are only viewed needs when I filter for unviewed needs then I expect to see a "no results found" message
given that I reset the filters when I clear the viewed/unviewed filter then I expect to see all available needs again
**NOT IMPLEMENTED YET** As a Helper, I would like to filter my searches by price so I can view needs within my current budget. | given that needs exist with different prices when I filter by a specific price range then I expect to see only the needs within that range
given that no needs exist within the selected price range when I filter by that range then I expect to see a "no results found" message
given that I reset the filters when I clear the price filter then I expect to see all available needs again